## 📊 Dashboard
🏥 AROGGA – Reverse Engineer Tracker ¦ Full Feature Build Plan
Bangladesh's leading online pharmacy clone ¦ Medicine · Beauty · Healthcare · Lab Tests · Doctor Consultation
Project | Arogga Clone – Healthcare eCommerce Platform
Started | 15 Apr 2026
Target Stack | Next.js · NestJS · PostgreSQL · Redis · Elasticsearch
Payment GW | bKash · Nagad · SSLCommerz · Card
Lead Dev
Version | v1.0
Module | Total Features | Done | In Progress | Next | Pending | Completion %
Frontend – Core Pages & UI | 0 | 0 | 0 | 0 | 0 | 0
Frontend – User Account & Orders | 0 | 0 | 0 | 0 | 0 | 0
Frontend – Pharmacy-Specific | 0 | 0 | 0 | 0 | 0 | 0
Backend Admin Panel | 0 | 0 | 0 | 0 | 0 | 0
Backend – Sales Manager Panel | 0 | 0 | 0 | 0 | 0 | 0
Mobile App Features | 0 | 0 | 0 | 0 | 0 | 0
Facebook Pixel & Analytics | 0 | 0 | 0 | 0 | 0 | 0
Payment & Integrations | 0 | 0 | 0 | 0 | 0 | 0
SEO & Performance | 0 | 0 | 0 | 0 | 0 | 0
Security & Compliance | 0 | 0 | 0 | 0 | 0 | 0
📌 HOW TO USE THIS TRACKER
• Update the '📋 Feature Log' sheet as you build each feature. Change Status from Pending → In Progress → Done.
• Priority: High = must-have for MVP ¦ Medium = important but can delay ¦ Low = nice-to-have
• % of Done column: fill 0–100 per feature for granular tracking
• Facebook Pixel events are in the '📣 FB Pixel & Analytics' sheet — tick off each event as you implement
• Tech Stack decisions are documented in '🛠 Tech Stack' sheet with rationale
• Implementation Roadmap with sprint planning is in '🗺 Roadmap' sheet

## 📋 Feature Log
📋Complete Feature Log
Section | Feature / Task | Priority | Status | % Done | Done Date | Due Date | Tech Notes / Comment
🖥️ FRONTEND — Core Pages & Navigation
Frontend | Homepage — Hero Banner / Carousel Slider (dynamic from admin) | High | Pending | 0 |  |  | Auto-rotating, clickable banners. CMS-driven.
Frontend | Homepage — Flash Sale section with countdown timer | High | Pending | 0 |  |  | Real-time countdown, filtered product cards
Frontend | Homepage — Category icon strip (Medicine, Lab, Beauty, etc.) | High | Pending | 0 |  |  | 12+ categories: Medicine, Lab Test, Healthcare, Beauty, Herbal…
Frontend | Homepage — Horizontal product row sliders (multiple sections) | High | Pending | 0 |  |  | Featured, Top-selling, New Arrivals rows
Frontend | Homepage — Promotional banner sections (mid-page ads) | Medium | Pending | 0 |  |  | Static/dynamic image banners from CMS
Frontend | Homepage — Brand logo strip / trusted brands carousel | Low | Pending | 0
Frontend | Product Listing / Category Page with filters | High | Pending | 0 |  |  | Filter by brand, price range, form, availability; sort options
Frontend | Product Detail Page — full info (generic name, manufacturer, uses, side effects, dose) | High | Pending | 0 |  |  | Expandable accordion sections; image gallery
Frontend | Product Detail Page — prescription-required badge & upload prompt | High | Pending | 0
Frontend | Product Detail Page — alternate brands / generic substitutes | Medium | Pending | 0 |  |  | Show cheaper generics for the same molecule
Frontend | Product Detail Page — Related products & Recently viewed | Medium | Pending | 0
Frontend | Product Detail Page — Rating & Reviews section | Medium | Pending | 0
Frontend | Search bar — Autocomplete with medicine/brand/generic name | High | Pending | 0 |  |  | Elasticsearch-powered; suggest as you type
Frontend | Search results page with filters and sorting | High | Pending | 0
Frontend | Prescription Upload page — drag & drop / camera capture | High | Pending | 0 |  |  | Pharmacist reviews before confirming order
Frontend | Cart page — item list, qty change, remove, coupon, subtotal | High | Pending | 0
Frontend | Checkout — address selection / new address, delivery slot, payment | High | Pending | 0
Frontend | Order Confirmation page + email/SMS notification | High | Pending | 0
Frontend | Order Tracking page — live status steps | High | Pending | 0
Frontend | Medicine category-home page (A-Z index, popular brands) | Medium | Pending | 0
Frontend | Lab Test listing & booking page | High | Pending | 0 |  |  | Filter by test name, package; select collection date & slot
Frontend | Doctor Consultation page — specialist listing, booking flow | Medium | Pending | 0
Frontend | Blog / Health Articles page | Low | Pending | 0
Frontend | About Us page | Low | Pending | 0
Frontend | Contact Us page + live chat widget | Low | Pending | 0
Frontend | FAQ / Help Center page | Low | Pending | 0
Frontend | Return & Refund Policy page | Low | Pending | 0
Frontend | Footer — links, app download badges, social icons, hotline | Medium | Pending | 0
Frontend | Mobile Responsive — all pages (320px–1440px) | High | Pending | 0
Frontend | Dark Mode support | Low | Pending | 0
Frontend | Bengali language toggle (BN/EN) | Medium | Pending | 0
Frontend | Sticky header with cart count & search | Medium | Pending | 0
Frontend | Breadcrumb navigation on all inner pages | Low | Pending | 0
Frontend | 404 / Error pages | Low | Pending | 0
👤 FRONTEND — User Account & Auth
User Account | Phone number OTP Sign-up flow | High | Pending | 0 |  |  | 6-digit OTP via SMS; resend timer
User Account | Login with phone + OTP / password | High | Pending | 0
User Account | Social Login — Google / Facebook | Medium | Pending | 0
User Account | Forgot password / Reset via OTP | High | Pending | 0
User Account | User Dashboard — overview (orders, prescriptions, points) | High | Pending | 0
User Account | Order History — list, search, re-order | High | Pending | 0
User Account | Order Detail — items, timeline, invoice download | High | Pending | 0
User Account | Cancel Order flow | High | Pending | 0
User Account | Return/Refund Request flow | Medium | Pending | 0
User Account | Saved Prescriptions library | High | Pending | 0 |  |  | User can save & reuse prescriptions
User Account | Address Book — add/edit/delete multiple addresses | High | Pending | 0
User Account | Wishlist / Saved items | Medium | Pending | 0
User Account | Loyalty Points / Reward Balance display | Medium | Pending | 0
User Account | Referral program — unique code, earnings | Medium | Pending | 0
User Account | Profile edit — name, email, DOB, gender | Medium | Pending | 0
User Account | Change password | Medium | Pending | 0
User Account | Notification preferences (SMS/Email toggle) | Low | Pending | 0
User Account | Lab Test bookings history | Medium | Pending | 0
User Account | Doctor consultation history | Medium | Pending | 0
💊 FRONTEND — Pharmacy-Specific Features
Pharmacy | Medicine search by generic name / brand / manufacturer | High | Pending | 0
Pharmacy | Drug interaction checker | Low | Pending | 0 |  |  | Future feature — Phase 2
Pharmacy | Prescription-required medicine gating | High | Pending | 0 |  |  | Cannot checkout Rx meds without valid prescription
Pharmacy | Pharmacist prescription review notification to admin | High | Pending | 0
Pharmacy | Medicine reorder reminder (chronic patients) | Medium | Pending | 0
Pharmacy | OTC vs Prescription product badge | Medium | Pending | 0
Pharmacy | Medicine price comparison (generic vs branded) | Medium | Pending | 0
Pharmacy | Dosage & usage information (patient-friendly) | Medium | Pending | 0
Pharmacy | Stock availability badge (In Stock / Out of Stock / Limited) | High | Pending | 0
Pharmacy | Cold-chain / refrigerated medicine label | Low | Pending | 0
⚙️ BACKEND — Admin Control Panel
Admin | Admin login with 2FA (TOTP/SMS) | High | Pending | 0
Admin | Dashboard KPIs — GMV, orders, revenue, new users (today/week/month) | High | Pending | 0
Admin | Dashboard — charts: sales trend, category split, top products | High | Pending | 0
Admin | Real-time order notifications (browser push + sound) | High | Pending | 0
Admin | Product Management — Create / Edit / Delete | High | Pending | 0 |  |  | Generic name, brand, manufacturer, form, strength, images, price, MRP
Admin | Product — bulk import via CSV/Excel | Medium | Pending | 0
Admin | Product — SEO fields (meta title, description, slug) | Medium | Pending | 0
Admin | Product — variant management (size, pack, strength) | High | Pending | 0
Admin | Product — image upload with CDN (multiple images) | High | Pending | 0
Admin | Product — mark as prescription-required | High | Pending | 0
Admin | Category & Sub-category Management (CRUD + icon upload) | High | Pending | 0
Admin | Brand Management (CRUD + logo) | Medium | Pending | 0
Admin | Manufacturer Management | Medium | Pending | 0
Admin | Inventory / Stock Management — current stock, low-stock alerts | High | Pending | 0
Admin | Stock in / Stock out log | High | Pending | 0
Admin | Order Management — list with filters (date, status, payment, area) | High | Pending | 0
Admin | Order Detail — view items, customer info, prescription, change status | High | Pending | 0
Admin | Order status pipeline — Pending → Confirmed → Processing → Shipped → Delivered / Cancelled | High | Pending | 0
Admin | Order — assign delivery agent | Medium | Pending | 0
Admin | Order — print invoice / receipt (thermal / A4) | Medium | Pending | 0
Admin | Order — generate invoice PDF | Medium | Pending | 0
Admin | Order — edit (add/remove item, adjust qty) | Medium | Pending | 0
Admin | Prescription Review Queue — approve / reject | High | Pending | 0
Admin | Refund & Return Management | High | Pending | 0
Admin | Customer Management — list, profile, order history, block | High | Pending | 0
Admin | Coupon / Promo Code Management — CRUD | High | Pending | 0 |  |  | Type: flat/percent, applicable to product/category/user/all
Admin | Coupon — date validity, min order value, usage limit | High | Pending | 0
Admin | Flash Sale Management — schedule, products, discount % | High | Pending | 0
Admin | Banner / Slider Management — upload, schedule, link, order | High | Pending | 0
Admin | Home Page Section Manager — enable/disable/reorder sections (drag-drop) | High | Pending | 0
Admin | Delivery Zone & Charge Setup (area-wise pricing) | High | Pending | 0
Admin | Delivery Slot Management | Medium | Pending | 0
Admin | Payment Gateway Config — bKash, Nagad, SSLCommerz, Card | High | Pending | 0
Admin | SMS Gateway Config (Green Web / SSL Wireless) | High | Pending | 0
Admin | Email Configuration (SMTP / SendGrid) | High | Pending | 0
Admin | Push Notification — send to all / segment | Medium | Pending | 0
Admin | Lab Test Management — tests, packages, pricing, partner labs | High | Pending | 0
Admin | Lab Test Booking Management — assign phlebotomist, update status | High | Pending | 0
Admin | Doctor Management — profile, specialty, schedule, fee | Medium | Pending | 0
Admin | Doctor Consultation Booking Management | Medium | Pending | 0
Admin | User Role & Permission Management (Admin, Pharmacist, Sales, Delivery) | High | Pending | 0
Admin | Review & Rating Moderation — approve / reject / reply | Medium | Pending | 0
Admin | Blog / Article Management (CMS) | Low | Pending | 0
Admin | FAQ Management | Low | Pending | 0
Admin | SEO Manager — meta tags per page/product/category | Medium | Pending | 0
Admin | Reports — Sales by day/week/month (export CSV/PDF) | High | Pending | 0
Admin | Reports — Inventory report | High | Pending | 0
Admin | Reports — Customer report (new, returning, LTV) | Medium | Pending | 0
Admin | Reports — Top products / Categories | Medium | Pending | 0
Admin | Reports — Coupon usage report | Medium | Pending | 0
Admin | Loyalty / Points System Config | Medium | Pending | 0
Admin | Referral Program Config | Medium | Pending | 0
Admin | Supplier / Vendor Management | Medium | Pending | 0
Admin | Activity Log / Audit Trail | Medium | Pending | 0
Admin | System Settings — site name, logo, contact, tax, currency | High | Pending | 0
🧑‍💼 BACKEND — Sales Manager Panel
Sales Manager | Sales Manager login (role-restricted) | High | Pending | 0
Sales Manager | Live order notification dashboard | High | Pending | 0
Sales Manager | Order list — view, filter by status & date | High | Pending | 0
Sales Manager | Update order status (Confirmed → Processing → Shipped) | High | Pending | 0
Sales Manager | Print order receipt / packing slip | High | Pending | 0
Sales Manager | Prescription review & approval | High | Pending | 0
Sales Manager | Daily sales summary report | Medium | Pending | 0
Sales Manager | Generate order invoice PDF | Medium | Pending | 0
Sales Manager | Call customer for order confirmation | Low | Pending | 0
Sales Manager | Session management (auto-logout after inactivity) | Medium | Pending | 0
📱 MOBILE APP — Android & iOS
Mobile App | App architecture — React Native or Flutter (cross-platform) | High | Pending | 0 |  |  | Recommend React Native for code-sharing with Next.js
Mobile App | Onboarding screens — splash, walkthrough, OTP login | High | Pending | 0
Mobile App | Home screen — mirrors website with native UX | High | Pending | 0
Mobile App | Camera-based prescription upload | High | Pending | 0
Mobile App | Push notifications — order status, flash sale, reorder reminder | High | Pending | 0
Mobile App | Deep linking — product pages, offers | Medium | Pending | 0
Mobile App | Offline mode — show cached products/orders | Low | Pending | 0
Mobile App | In-app chat with pharmacist | Medium | Pending | 0
Mobile App | bKash / Nagad SDK payment integration | High | Pending | 0
Mobile App | Location-based delivery area detection | Medium | Pending | 0
Mobile App | App Store & Play Store listing assets (icon, screenshots, copy) | Medium | Pending | 0
Mobile App | App version force-update mechanism | Medium | Pending | 0
Mobile App | Biometric login (fingerprint/FaceID) | Low | Pending | 0
Mobile App | Rating prompt after delivery | Low | Pending | 0
Mobile App | Referral share via WhatsApp / Facebook / copy link | Medium | Pending | 0
Mobile App | Lab test booking in-app | High | Pending | 0
Mobile App | Doctor consultation in-app (video/chat) | Medium | Pending | 0
Mobile App | Health profile — allergies, chronic conditions, saved medicines | Medium | Pending | 0

## 📣 FB Pixel & Analytics
📣 Facebook Pixel & Analytics Implementation Plan
Event / Tag | Trigger Point | Parameters to Pass | Where in Code | Priority | Status | Notes
Base Pixel Code | Every page load | N/A | _app.tsx / <Head> component | High | Pending | Install via next-third-parties or react-facebook-pixel
PageView | Every route change | URL, page title | _app.tsx → router.events.on('routeChangeComplete') | High | Pending | Automatic after base pixel
ViewContent | Product detail page load | content_ids, content_name, content_type, value, currency | pages/product/[slug].tsx — useEffect on mount | High | Pending | content_type: 'product'
Search | User submits search query | search_string | Search component onSubmit | High | Pending | Fire when search results page loads
AddToCart | User clicks 'Add to Cart' button | content_ids, content_name, content_type, value, currency, num_items | CartButton onClick handler | High | Pending | Fire before or after API call succeeds
AddToWishlist | User clicks wishlist/heart icon | content_ids, content_name, value, currency | WishlistButton onClick | Medium | Pending
InitiateCheckout | User reaches checkout page | content_ids, num_items, value, currency | pages/checkout.tsx — useEffect | High | Pending | Include all cart item IDs
AddPaymentInfo | User selects payment method & proceeds | value, currency, content_ids | Checkout → payment step component | High | Pending
Purchase | Order confirmation page load | purchase_id (order_id), value, currency, content_ids, num_items | pages/order-success/[id].tsx — useEffect | High | Pending | MOST IMPORTANT — verify no duplicates; use order_id dedup
Lead | User completes prescription upload | content_name: 'prescription_upload' | Upload success callback | Medium | Pending
CompleteRegistration | User completes OTP verification & account created | status: 'completed', currency, value: 0 | Auth success handler | High | Pending
Contact | User submits Contact Us form | N/A | ContactForm onSubmit success | Low | Pending
LabTestBooking (Custom) | User books a lab test | content_name: test_name, value, currency | Lab test booking confirmation | High | Pending | Custom event — trackCustomEvent('LabTestBooking', {...})
DoctorBooking (Custom) | User books doctor consultation | content_name: doctor_name, value, currency | Consultation booking confirmation | Medium | Pending | Custom event
PrescriptionUploaded (Custom) | Prescription upload complete | num_pages | Upload API success | Medium | Pending | Custom event
── CAPI (Server-Side) ──
Server-Side Purchase Event | Order placed on backend | Same as client Purchase + IP, user_agent, fbc, fbp | NestJS order.service.ts → after order saved | High | Pending | Use Facebook Conversions API for better attribution & iOS14+ accuracy
Server-Side Lead | Prescription submitted (backend confirm) | event_name, user data hashed | NestJS prescription.service.ts | Medium | Pending | Hash email & phone with SHA256
── Google Analytics 4 ──
GA4 Base (gtag.js) | Every page | measurement_id | _app.tsx | High | Pending | Use GA4 not UA
GA4 purchase event | Order confirmed | transaction_id, value, currency, items[] | Order success page | High | Pending
GA4 add_to_cart | Add to cart | item_id, item_name, price, quantity | Cart button | High | Pending
GA4 view_item | Product detail page | item_id, item_name, price, item_category | Product page | High | Pending
GA4 begin_checkout | Checkout page | value, currency, items[] | Checkout page | High | Pending
── Hotjar / Clarity ──
Hotjar Heatmaps | All pages | N/A | _app.tsx | Medium | Pending | UX insights
Microsoft Clarity | All pages | N/A | _app.tsx | Low | Pending | Free alternative to Hotjar

## 🛠 Tech Stack
🛠 Recommended Technology Stack — Arogga Clone
Layer | Technology | Version / Service | Why This Choice | Alternative | Status
── FRONTEND ──
Web Framework | Next.js (React) | v14+ (App Router) | SSR+SSG for SEO, fast page loads; Vercel deploy; perfect for product pages | Nuxt.js (Vue) | Chosen
Language | TypeScript | v5+ | Type safety reduces bugs; better IDE support for large codebase | JavaScript (plain) | Chosen
Styling | Tailwind CSS | v3+ | Utility-first, fast to build, consistent design tokens | styled-components / MUI | Chosen
UI Components | shadcn/ui + Radix UI | Latest | Accessible, composable, no dependency lock-in | Ant Design | Chosen
State Management | Zustand + React Query | Latest | Zustand for global UI state; React Query for server state & caching | Redux Toolkit | Chosen
Forms | React Hook Form + Zod | Latest | Performant, schema-based validation | Formik + Yup | Chosen
Animations | Framer Motion | Latest | Smooth page transitions and micro-interactions | CSS animations | Chosen
Image CDN | Cloudinary or AWS CloudFront | — | Image resize on-the-fly, WebP conversion, CDN distribution | imgix | Evaluate
── MOBILE APP ──
App Framework | React Native (Expo) | SDK 51+ | Code-sharing with web (hooks, utils); large community; Expo OTA updates | Flutter | Chosen
Navigation | React Navigation v6 | Latest | De-facto standard for React Native routing | Expo Router | Chosen
Push Notifications | Firebase Cloud Messaging (FCM) | — | Free, reliable, supports Android+iOS | OneSignal | Chosen
── BACKEND ──
Backend Framework | NestJS (Node.js) | v10+ | Modular architecture, TypeScript-native, decorator-based, scales well; mirrors Angular concepts | Express.js / Laravel (PHP) | Chosen
API Style | REST + GraphQL (optional) | — | REST for mobile app; GraphQL for dashboard if complex queries | REST only | Chosen
Real-time | Socket.io | v4+ | Live order notifications, chat with pharmacist | SSE / WebSockets | Chosen
Task Queue | BullMQ (Redis-backed) | Latest | Background jobs: emails, SMS, order processing, report generation | Celery / RabbitMQ | Chosen
Cron Jobs | NestJS Schedule (@nestjs/schedule) | — | Flash sale start/end, stock alerts, report emails | node-cron | Chosen
── DATABASE ──
Primary DB | PostgreSQL | v16+ | ACID compliant, relational, great for orders/users/inventory; JSON support | MySQL | Chosen
ORM | Prisma | v5+ | Type-safe queries, auto-migration, excellent DX with TypeScript | TypeORM / Sequelize | Chosen
Cache / Session | Redis | v7+ | Session store, cart cache, rate limiting, pub/sub for notifications | Memcached | Chosen
Search Engine | Elasticsearch / OpenSearch | v8+ | Full-text search across 50k+ medicines; autocomplete; filters | Algolia (paid) | Chosen
File Storage | AWS S3 (or DigitalOcean Spaces) | — | Prescriptions, product images, invoices — scalable object storage | Cloudinary | Chosen
── PAYMENT GATEWAYS ──
Mobile Banking | bKash Payment Gateway | API v1.2 | Most popular MFS in Bangladesh; required for BD market | — | Integrate
Mobile Banking | Nagad Payment Gateway | Latest API | 2nd largest MFS; growing user base | — | Integrate
Card / Internet | SSLCommerz | Latest | Supports VISA/Master/Amex/net banking; most widely used in BD | ShurjoPay | Integrate
International | Stripe (optional) | Latest | For future international orders | PayPal | Future
COD | Cash on Delivery logic | Custom | Still dominant in BD; handle via order management system | — | Integrate
── COMMUNICATIONS ──
SMS Gateway | Green Web BD / SSL Wireless | REST API | Local SMS providers for OTP & order notifications in Bangladesh | Twilio (expensive for BD) | Chosen
Email | SendGrid / AWS SES | Latest | Transactional emails — order confirm, invoice, OTP fallback | Mailgun | Chosen
── DEVOPS & INFRASTRUCTURE ──
Cloud Provider | AWS (or DigitalOcean for cost) | — | EC2/App Runner for backend; S3 for storage; CloudFront CDN | GCP / Azure | Chosen
Containerization | Docker + Docker Compose | Latest | Consistent dev/prod environments; easy CI/CD | Podman | Chosen
Orchestration | AWS ECS or Kubernetes (k3s) | — | Auto-scaling; zero-downtime deploys | Render.com | Evaluate
CI/CD | GitHub Actions | — | Free for public repos; automated test → build → deploy pipeline | GitLab CI | Chosen
Frontend Deploy | Vercel | — | Zero-config Next.js deploy; edge functions; CDN included | Netlify / AWS Amplify | Chosen
Monitoring | Grafana + Prometheus | — | Metrics, dashboards, alerting for backend services | Datadog (costly) | Evaluate
Error Tracking | Sentry | Latest | Real-time error alerts for both frontend and backend | Bugsnag | Chosen
Logging | Winston + ELK Stack | — | Structured logging; search through logs in Kibana | Papertrail | Evaluate
── SECURITY ──
Auth | JWT (Access + Refresh tokens) + Passport.js | — | Stateless auth; refresh token rotation for security | Session-based auth | Chosen
Rate Limiting | NestJS Throttler + Redis | — | Prevent brute-force on OTP & login endpoints | — | Chosen
WAF | AWS WAF / Cloudflare | — | Block malicious traffic, DDoS protection | — | Evaluate
HTTPS | Let's Encrypt (auto via Nginx) | — | Free SSL; auto-renewal | AWS ACM | Chosen
Data Encryption | bcrypt (passwords) + SHA256 (FB Pixel hashing) | — | Never store plain passwords | — | Chosen
GDPR/PDPA | Cookie consent banner, data deletion endpoint | — | Compliance with Bangladesh data protection guidelines | — | Plan

## 🗺 Roadmap
🗺 Implementation Roadmap — Arogga Clone (Agile Sprint Plan)
Phase | Sprint | Duration | Key Deliverables | Teams | Status | Notes
Phase 0 Foundation | Sprint 0 | 1 week | ✔ Repo setup (monorepo: apps/web, apps/api, apps/mobile) ✔ Docker Compose dev env ✔ DB schema design (Prisma) ✔ CI/CD pipeline (GitHub Actions) ✔ Figma design system setup | DevOps, Backend, Design | Pending | Do NOT skip this sprint. Design DB schema carefully — changes later are expensive.
Phase 1 MVP Core | Sprint 1 | 2 weeks | ✔ Product catalog (CRUD API + listing FE) ✔ Category system ✔ Product detail page ✔ Search (basic — DB full-text) ✔ Admin: product management | Backend, Frontend | Pending | Use PostgreSQL full-text search before Elasticsearch for speed
Phase 1 MVP Core | Sprint 2 | 2 weeks | ✔ User auth (OTP login, JWT) ✔ Cart system ✔ Checkout flow (address, COD) ✔ Order placement API ✔ Basic order management admin ✔ Email/SMS notifications | Backend, Frontend | Pending | COD first; card payments in Phase 2
Phase 1 MVP Core | Sprint 3 | 2 weeks | ✔ Prescription upload (S3 storage) ✔ Pharmacist review queue (admin) ✔ Order status pipeline & tracking FE ✔ User dashboard (orders, profile, addresses) ✔ Homepage — banners, category strip, product rows | Backend, Frontend | Pending
Phase 2 Growth | Sprint 4 | 2 weeks | ✔ bKash + Nagad payment integration ✔ SSLCommerz card payment ✔ Coupon / promo code system ✔ Flash sale module ✔ Wishlist ✔ Product reviews & ratings | Backend, Frontend | Pending | Payment integrations need merchant account first — apply early!
Phase 2 Growth | Sprint 5 | 2 weeks | ✔ Elasticsearch integration (autocomplete, advanced search) ✔ Lab test module (listing, booking API, admin management) ✔ Delivery zone & charge system ✔ Facebook Pixel base + core events (PageView, AddToCart, Purchase) ✔ Google Analytics 4 | Backend, Frontend, Analytics | Pending
Phase 2 Growth | Sprint 6 | 2 weeks | ✔ Mobile app — React Native scaffold ✔ Mobile: auth, home, product listing, cart, checkout ✔ Mobile: push notifications (FCM) ✔ Admin: reports & analytics dashboards ✔ Role & permission system | Mobile, Backend | Pending
Phase 3 Scale | Sprint 7 | 2 weeks | ✔ Doctor consultation module ✔ Loyalty / points system ✔ Referral program ✔ Blog / health articles CMS ✔ Server-side Facebook Conversions API ✔ Performance optimization (Redis caching, DB indexing) | Backend, Frontend | Pending
Phase 3 Scale | Sprint 8 | 2 weeks | ✔ Advanced admin reports (PDF/Excel export) ✔ Inventory management (low-stock alerts, supplier management) ✔ Return/refund workflow ✔ SEO optimization (sitemap, schema markup, meta tags) ✔ PWA support for web | Backend, Frontend, DevOps | Pending
Phase 4 Launch | Sprint 9 | 2 weeks | ✔ QA & bug fixing (full regression) ✔ Load testing (k6 / Artillery) ✔ Security audit (OWASP checklist) ✔ Staging → Production deploy ✔ Play Store & App Store submission ✔ LegitScript certification process | All Teams, QA | Pending | LegitScript cert is mandatory for running pharmacy ads on Google/Meta in Bangladesh
Phase 4 Launch | Sprint 10 | Ongoing | ✔ Post-launch monitoring (Sentry, Grafana) ✔ A/B testing (product pages, checkout) ✔ Conversion rate optimization ✔ Customer feedback loop ✔ Feature iterations based on data | All Teams | Pending
💡 KEY ECOMMERCE LOGIC DECISIONS
Pricing Model | Store MRP separately from selling_price. Discount = (MRP - selling_price) / MRP. Show both on product card for perceived value.
Cart Architecture | Server-side cart (DB/Redis) — not just localStorage. This enables: cross-device sync, server-side coupon validation, and correct inventory deduction at checkout.
Inventory Deduction | Reserve stock at 'Add to Cart' (soft hold with TTL 15 min). Confirm deduction only when payment succeeds. Release hold on cart abandon or timeout.
Prescription Flow | Gate Rx medicines at checkout — not at add-to-cart. Prompt upload if cart contains Rx items. Pharmacist approves before order is confirmed.
Payment Flow | Redirect to payment gateway → webhook confirms payment → order status updated. NEVER trust frontend for payment confirmation. Always verify on server via gateway webhook.
Coupon Validation | All coupon logic must happen server-side. Client shows discounted price optimistically but final price is recalculated on server at checkout.
Order Numbering | Use human-readable order IDs (e.g., ARG-2025-001234) — easier for customer support. Store auto-increment ID internally.
Search Strategy | Phase 1: PostgreSQL full-text search (ts_vector). Phase 2: Elasticsearch with synonym dictionary for medicine names (paracetamol = Napa = Ace = Paracet).
Multi-address | Users can have multiple addresses (home, office, family). Each order uses one delivery address. Support location pin via Google Maps API.
Notifications | Trigger: Order placed → SMS + Email. Status change → SMS. Delivered → SMS + push. Use a notification service (NestJS microservice with BullMQ queue).